Adopted 2045 CompREHENSIVE Plan uPDATE Time Frame

Amended January 10, 2023		Adopted February 2, 2023

| Time Frame | Phases of Plan Development | Responsibility |
| --- | --- | --- |
| November 2022 – April 2023 | Phase 1: 2045 Plan Start Up/Organization *PC Meeting 12/13/23 *PC Meeting 1/10/23 *Joint PC/CC Meeting 2/2/23 | CC/PC/Staff |
| November 2022 – April 2023 | Phase 2: Existing Conditions Data Collection, Mapping and Trends Analysis | Staff |
| May 2023 – June 2023 | Phase 3: Strength, Weakness, Opportunity, Threat (SWOT) Analysis/Visioning *1st Public Input Meeting: week of June 5, 2023 | PC/Staff |
| July 2023 – September 2023 | Phase 4: Goals and Objectives *Goals and Objectives Public Survey *County Fair Mapping Activity & Goals and Objectives: Week of August 21, 2023 *2nd Public Input Meeting: week of August 28, 2023 *Joint PC/CC Meeting 9/21/23 | CC/PC/Staff |
| October 2023 – May 2024 | Phase 5: Plan Recommendations and Implementation Strategies *Land Use Public Survey *3rd Public Input Meeting: 3rd/4th week of January 2024 *4th Public Input Meeting: late April 2024 | PC/Staff |
| June 2024 – December 2024 | Phase 6: Plan Adoption *PC Public Hearing: tentative 7/23/24 *CC Public Hearing: tentative 10/17/24 Tentative Approval: 12/5/24 | CC/PC/Staff |

PC - Planning Commission

CC – County Commission

Highlighted in Purple – Planning or County Commission Regular Meeting

Highlighted in Green – Public Input Meeting

Highlighted in Orange – Public Survey

| Tentative Dates | Tasks | Responsibility |
| --- | --- | --- |
| November 2022 – April 2023 | Phase 1: 2045 Plan Start Up/Organization |  |
| November 2022 - January 2023 | Research Comp Plan methodologies and scope of work | Staff |
| December 2022 | Staff Organizing - Draft potential Timeline, Budget, PC Scope of work, Strategy | Staff |
| 12/13/22 | Planning Commission Meeting - Discuss tasks for PC - Review proposed scope, timeline, committees - Request PC Strength, Weakness, Opportunity, Threat (SWOT) exercise for January 10, 2023 - Request Joint PC/CC Meeting for February 26, 2023 | PC/Staff |
| 1/10/2023 | Planning Commission Meeting SWOT Exercise for PC to start initial guidance | PC/Staff |
| 2/2/23 (tentative) | Joint PC/CC Meeting: - Introduce Comp Plan Process and Requirements (WV 8A) - Propose 2045 Comprehensive Plan Timeline, Scope of Work, and Strategy - Discussion of PC additional meeting commitment and plan elements - SWOT Exercise for CC&PC to start initial guidance | CC/PC/Staff |
| February 2023 -April 2023 | PC Work Sessions: - Review existing plan recommendations and status of implementation - Review Staff findings from Phase 2 Existing Conditions, Data Collection, Mapping, and Trend Analysis - Establish Public Outreach Strategy including establishing/confirming format, locations, outreach effort for required public input meetings | PC/Staff |
| November 2022 – April 2023 | Phase 2: Existing Conditions Data Collection, Mapping and Trends Analysis |  |  |
| November 2022 – April 2023 | Compiling and evaluating existing conditions/background data such as: demographic, economic, community facilities. Analyze existing land use map/data gathering (coordinating with Office of GIS on available data) - Demographic Data – (Data Inventory and Analysis) - Existing Land Use map/data Gathering - Natural and Cultural Resources - Growth and Livability - Housing Stock, Transportation, Infrastructure - Schools, Parks - Resiliency - Stormwater management, EMS and Safety Services, Green Building - Economic Development - Employment and Commuting data, Tourism - Alternative Energy - Rural Economy and Agriculture | Staff |  |
| January – April 2023 | Carry out Data Collection Meetings - Incorporated Cities, Higher Education Institutions - Transportation, Utilities, School Board - Emergency Services and Economic Development - Parks, Historic, Cultural, Natural Resource groups | Staff |  |

| May 2023 – June 2023 | Phase 3: SWOT Analysis/Visioning |  |
| --- | --- | --- |
| May 23, 2023 | PC Work Session: - Review of Existing Conditions Data, Mapping and Trend Analysis developed by staff to date - Preparation for 1st Public Input Meeting | PC/Staff |
| Week of June 5th, 2023 | Kick-Off Meetings: 1st Public Input Meeting - Review of Existing Conditions and Data - SWOT Analysis -- identification and analysis - Visioning exercise | PC/Staff |
| June 27, 2023 | PC Work Session: - Visioning Activity - Review and synthesize SWOT analysis, visioning input - Initiate development of draft goals and objectives | PC/Staff |

| July 2023 – September 2023 | Phase 4: Goals and Objectives |  |
| --- | --- | --- |
| Mid-June to Mid-July 2023 | - Release Goals and Objectives Online Survey - Begin public outreach for survey completion | Staff |
| July 2023 -August 2023 | PC Work Sessions: - Synthesize results of the SWOT analysis and data; potential topics below - Growth and Livability, Housing and Infrastructure - Transportation, Resiliency - Economic Development and Employment - Develop draft Goals and Objectives/Action Items - Preparation for County Fair and 2nd Public Input Meeting | PC/Staff |
| Week of August 21st, 2023 | COUNTY FAIR WEEK - Land Use Exercise - Goals and Objectives Survey | PC/Staff |
| Week of August 28th, 2023 | 2nd Public Input Meeting - “What We Heard” (in June) - Draft Goals and Objectives presentation and feedback - Initial Future Land Use visioning exercise and related infrastructure | PC/Staff |
| September 26, 2023 | PC Work Session: - Preparation for Joint PC/CC Meeting on Goals and Objectives | PC/Staff |
| End of September 2023 | Joint meeting of PC/CC to request endorsement of Goals and Objectives – need legal input | CC/PC Staff/Legal |

| October 2023 - May 2024 | Phase 5: Plan Recommendations and Implementation Strategies |  |
| --- | --- | --- |
| October 2023 – January 2024 | PC Work Sessions: - Drafting text and future maps for plan elements based on approved Goals and Objectives, Draft of SWOT Action Items - Preparation for 3rd Public Input Meeting | PC/Staff |
| October 2023 | - Release Land Use Online Survey - Begin public outreach for survey completion | Staff |
| Week of January 22nd, 2024 | 3rd Public Input Meeting - Review approved Goals and Objectives - “What We Heard” (in October) - Review draft recommendations, strategies, and action items - Finalize future land use map | PC/Staff |
| February 2024 – April 2024 | PC Work Sessions: - Finalize text and map recommendations available for public review - Preparation for 4rd Public Input Meeting | PC/Staff |
| Week of April 22nd, 2024 | 4th Public Input Meeting **Invite CC to this meeting | CC/PC/Staff |

| June 2024 – December 2024 | Phase 6: 2024 Plan Adoption |  |
| --- | --- | --- |
| 6/11/24 | PC Vote to Schedule PH – 30 days’ notice in local paper required | PC/Staff |
| 6/25/24 (PC 4th Tuesday Regular meeting) | PC Workshop – consensus to release version for public review | PC/Staff |
| 7/1/2024 | Release Version for Public Review | Staff |
| 7/23/24 (PC 4th Tuesday Regular Meeting) | PC Public Hearing Public Comments open for 2 weeks (8/6/24) | PC/Staff |
| 8/13/24 | PC review of comments received | PC/Staff |
| 8/27/24 (PC 4th Tuesday Regular Meeting) | PC Vote/Recommendation | PC/Staff |
| 9/5/24 | Recommendation forwarded to CC for scheduling of Workshop and Public Hearing (requires 15 days’ notice) | CC/Staff |
| 9/19/24 | County Commission Workshop | CC/PC/Staff |
| 10/17/24 | County Commission Public Hearing Public Comments open for 2 weeks (10/31/24) | CC/Staff |
| 11/7/24 | County Commission review of public comments received and final input and revisions | CC/Staff |
| 12/5/24 | County Commission Vote on 2045 Comprehensive Plan | CC |

All of these dates are subject to change*